## Current
Date | Q | A | Done Date
General
2014-04-15 | server, client start up bug | task not found for:garhttp://lhh.a8z8.com/forum.php?gid=1
2014-05-10 | Multi-thread Category Browsing | SiteB.start.level=2 SiteB.split.thread=true
2014-05-12 | Use Mapreduce to replace Task Manager

## Archive
Date | Q | A | Done Date
General
2014-04-10 | adding use javascript or not for all tasks |  | 2014-04-11
2014-04-15 | htmlunit Javascript engine dead lock | I am using the wrong version 2.11, 2.14 has this fixed | 2014-04-16
2014-04-15 | add ctonf.enableJSForItem |  | 2014-04-27
2014-04-27 | correct rerun.interim |  | 2014-04-27
Amazon
2014-04-08 | Regression Amazon China web site |  | 2002-04-08
2014-04-08 | Adding Amazon English web site support |  | 2014-04-11
LHH
2014-04-08 | Adding http://lhh.a8z8.com/portal.php support |  | 2014-04-11
2014-04-12 | lhh does not download the image, generate the book xml |  | 2014-04-12
2014-04-12 | Customize LHH also generate categoryxxx.xml |  | 2014-04-15
2014-04-23 | Using cat id and book id instead of name as the primary key |  | 2014-04-24
4.27.2014 | Added http://lianhuanhua.mom001.com/ support
2014-05-09 | Added DMZJ support
2014-04-15 | enable configuration for customized XXAnalyze | Using cconf parameters | 2014-05-09
2014-04-15 | hot deployment bug | java.lang.NullPointerException at org.cld.datastore.impl.DataStoreManagerImpl.getProductFromServer(DataStoreManagerImpl.java:368) | 2014-05-10

## Tests
ID | Conditions | Expected | Result

## Site Conf
Category
getSubCategoryList
getItemNum for this category
getCatId
List
getNextUrl
ProductList
List<Item> getItemList
getFullUrl (Item)
getInternalId for each product
Product
callbackReadDetails
getTitle